## Timeline
Project Name: Building House
Team:
Project Lead:
| Today's Date: | 2016-09-06 |  | (vertical red line)
[42] | Start Date: | 2016-06-15 | 2016-06-15 | [6 empty] | 0 | 2016-06-13 | 2016-06-14 | 2016-06-15 | 2016-06-16 | 2016-06-17 | 2016-06-20 | 2016-06-21 | 2016-06-22 | 2016-06-23 | 2016-06-24 | 2016-06-27 | 2016-06-28 | 2016-06-29 | 2016-06-30 | 2016-07-01 | 2016-07-04 | 2016-07-05 | 2016-07-06 | 2016-07-07 | 2016-07-08 | 2016-07-11 | 2016-07-12 | 2016-07-13 | 2016-07-14 | 2016-07-15 | 2016-07-18 | 2016-07-19 | 2016-07-20 | 2016-07-21 | 2016-07-22 | 2016-07-25 | 2016-07-26 | 2016-07-27 | 2016-07-28 | 2016-07-29 | 2016-08-01 | 2016-08-02 | 2016-08-03 | 2016-08-04 | 2016-08-05 | 2016-08-08 | 2016-08-09 | 2016-08-10 | 2016-08-11 | 2016-08-12 | 2016-08-15 | 2016-08-16 | 2016-08-17 | 2016-08-18 | 2016-08-19 | 2016-08-22 | 2016-08-23 | 2016-08-24 | 2016-08-25 | 2016-08-26 | 2016-08-29 | 2016-08-30 | 2016-08-31 | 2016-09-01 | 2016-09-02 | 2016-09-05 | 2016-09-06 | 2016-09-07 | 2016-09-08 | 2016-09-09 | 2016-09-12 | 2016-09-13 | 2016-09-14 | 2016-09-15 | 2016-09-16 | 2016-09-19 | 2016-09-20 | 2016-09-21 | 2016-09-22 | 2016-09-23 | 2016-09-26 | 2016-09-27 | 2016-09-28 | 2016-09-29 | 2016-09-30 | 2016-10-03 | 2016-10-04 | 2016-10-05 | 2016-10-06 | 2016-10-07 | 2016-10-10 | 2016-10-11 | 2016-10-12 | 2016-10-13 | 2016-10-14 | 2016-10-17 | 2016-10-18 | 2016-10-19 | 2016-10-20 | 2016-10-21 | 2016-10-24 | 2016-10-25 | 2016-10-26 | 2016-10-27 | 2016-10-28 | 2016-10-31 | 2016-11-01 | 2016-11-02 | 2016-11-03 | 2016-11-04 | 2016-11-07 | 2016-11-08 | 2016-11-09 | 2016-11-10 | 2016-11-11 | 2016-11-14 | 2016-11-15 | 2016-11-16 | 2016-11-17 | 2016-11-18 | 2016-11-21 | 2016-11-22 | 2016-11-23 | 2016-11-24 | 2016-11-25 | 2016-11-28 | 2016-11-29 | 2016-11-30 | 2016-12-01 | 2016-12-02 | 2016-12-05 | 2016-12-06 | 2016-12-07 | 2016-12-08 | 2016-12-09 | 2016-12-12 | 2016-12-13 | 2016-12-14 | 2016-12-15 | 2016-12-16 | 2016-12-19 | 2016-12-20 | 2016-12-21 | 2016-12-22 | 2016-12-23 | 2016-12-26 | 2016-12-27 | 2016-12-28 | 2016-12-29 | 2016-12-30 | 2017-01-02 | 2017-01-03 | 2017-01-04 | 2017-01-05 | 2017-01-06 | 2017-01-09 | 2017-01-10 | 2017-01-11 | 2017-01-12 | 2017-01-13 | 2017-01-16 | 2017-01-17 | 2017-01-18 | 2017-01-19 | 2017-01-20 | 2017-01-23 | 2017-01-24 | 2017-01-25 | 2017-01-26 | 2017-01-27 | 2017-01-30 | 2017-01-31 | 2017-02-01 | 2017-02-02 | 2017-02-03 | 2017-02-06 | 2017-02-07 | 2017-02-08 | 2017-02-09 | 2017-02-10 | 2017-02-13 | 2017-02-14 | 2017-02-15 | 2017-02-16 | 2017-02-17 | 2017-02-20 | 2017-02-21 | 2017-02-22 | 2017-02-23 | 2017-02-24 | 2017-02-27 | 2017-02-28 | 2017-03-01 | 2017-03-02 | 2017-03-03 | 2017-03-06 | 2017-03-07 | 2017-03-08 | 2017-03-09 | 2017-03-10 | 2017-03-13 | 2017-03-14 | 2017-03-15 | 2017-03-16 | 2017-03-17 | 2017-03-20 | 2017-03-21 | 2017-03-22 | 2017-03-23 | 2017-03-24 | 2017-03-27 | 2017-03-28 | 2017-03-29 | 2017-03-30 | 2017-03-31 | 2017-04-03 | 2017-04-04 | 2017-04-05 | 2017-04-06 | 2017-04-07 | 2017-04-10 | 2017-04-11 | 2017-04-12 | 2017-04-13 | 2017-04-14 | 2017-04-17 | 2017-04-18 | 2017-04-19 | 2017-04-20 | 2017-04-21 | 2017-04-24 | 2017-04-25 | 2017-04-26 | 2017-04-27 | 2017-04-28 | 2017-05-01 | 2017-05-02 | 2017-05-03 | 2017-05-04 | 2017-05-05 | 2017-05-08 | 2017-05-09 | 2017-05-10 | 2017-05-11 | 2017-05-12
WBS | Tasks | Task Lead | Start | End | Duration (Days) | % Complete | Working Days | Days Complete | Days Remaining | 2016-06-13: 2016-06-13; 2016-06-20: 2016-06-20; 2016-06-27: 2016-06-27; 2016-07-04: 2016-07-04; 2016-07-11: 2016-07-11; 2016-07-18: 2016-07-18; 2016-07-25: 2016-07-25; 2016-08-01: 2016-08-01; 2016-08-08: 2016-08-08; 2016-08-15: 2016-08-15; 2016-08-22: 2016-08-22; 2016-08-29: 2016-08-29; 2016-09-05: 2016-09-05; 2016-09-12: 2016-09-12; 2016-09-19: 2016-09-19; 2016-09-26: 2016-09-26; 2016-10-03: 2016-10-03; 2016-10-10: 2016-10-10; 2016-10-17: 2016-10-17; 2016-10-24: 2016-10-24; 2016-10-31: 2016-10-31; 2016-11-07: 2016-11-07; 2016-11-14: 2016-11-14; 2016-11-21: 2016-11-21; 2016-11-28: 2016-11-28; 2016-12-05: 2016-12-05; 2016-12-12: 2016-12-12; 2016-12-19: 2016-12-19; 2016-12-26: 2016-12-26; 2017-01-02: 2017-01-02; 2017-01-09: 2017-01-09; 2017-01-16: 2017-01-16; 2017-01-23: 2017-01-23; 2017-01-30: 2017-01-30; 2017-02-06: 2017-02-06; 2017-02-13: 2017-02-13; 2017-02-20: 2017-02-20; 2017-02-27: 2017-02-27; 2017-03-06: 2017-03-06; 2017-03-13: 2017-03-13; 2017-03-20: 2017-03-20; 2017-03-27: 2017-03-27; 2017-04-03: 2017-04-03; 2017-04-10: 2017-04-10; 2017-04-17: 2017-04-17; 2017-04-24: 2017-04-24; 2017-05-01: 2017-05-01; 2017-05-08: 2017-05-08
1 | Project Management |  | 2016-06-01 | 2017-02-12 | 257 | 28.74% | 183 | 73 | 184
1.1 | PM plan |  | 2016-06-01 | 2016-09-08 | 100 | 50% | 72 | 50 | 50
1.2 | Scope work |  | 2017-01-01 | 2017-01-14 | 14 |  | 10 | 0 | 14
1.3 | Plan resources |  | 2017-01-15 | 2017-02-13 | 30 |  | 21 | 0 | 30
1.4 | Plan materials |  | 2017-01-15 | 2017-02-13 | 30 |  | 21 | 0 | 30
[8 empty] | 0 | 0
2 | Foundation |  | 2017-01-15 | 2017-06-20 | 157 | 0% | 112 | 0 | 157 | bar: 0 to 2016-06-29
2.2 | Draw blueprint |  | 2017-01-15 | 2017-01-21 | 7 |  | 5 | 0 | 7
2.3 | Dig earth |  | 2017-06-01 | 2017-06-14 | 14 |  | 10 | 0 | 14
2.4 | Get material, labor |  | 2017-06-01 | 2017-06-07 | 7 |  | 5 | 0 | 7
2.5 | Lay foundation |  | 2017-06-15 | 2017-06-21 | 7 |  | 5 | 0 | 7
[8 empty] | 0 | 0
3 | Buidling Structure |  | 2017-06-15 | 2017-08-06 | 53 | 0% | 37 | 0 | 53 | bar: 0 to 2016-06-29
3.1 | Get materials |  | 2017-06-15 | 2017-06-21 | 7 |  | 5 | 0 | 7
3.2 | Construct pillars and beams |  | 2017-07-01 | 2017-07-10 | 10 |  | 6 | 0 | 10
3.3 | Construct walls |  | 2016-07-15 | 2016-07-28 | 14 |  | 10 | 0 | 14
3.4 | Finish plumbing work |  | 2017-08-01 | 2017-08-07 | 7 |  | 5 | 0 | 7
3.5 | Finish electrical work |  | 2017-08-01 | 2017-08-07 | 7 |  | 5 | 0 | 7
[8 empty] | 0 | 0
4 | Interiors |  | 2017-01-22 | 2017-10-30 | 282 | 0% | 201 | 0 | 282 | bar: 0 to 2016-06-29
4.1 | Design interiors |  | 2017-01-22 | 2017-02-15 | 25 |  | 18 | 0 | 25
4.2 | Decide furniture |  | 2017-10-01 | 2017-10-07 | 7 |  | 5 | 0 | 7
4.3 | Decide light fixtures |  | 2017-10-01 | 2017-10-07 | 7
4.4 | Procure furniture |  | 2017-10-15 | 2017-10-21 | 7
4.5 | Procure light fixtures |  | 2017-10-15 | 2017-10-21 | 7
4.6 | Fix lights, AC and fans |  | 2017-10-30 | 2017-10-31 | 2
5 | Landscaping |  | 2017-01-22 | 2017-11-04 | 287 | 0% | 205 | 0 | 287 | bar: 0 to 2016-06-29
5.1 | Design private, public areas |  | 2017-01-22 | 2017-02-15 | 25 |  | 18 | 0 | 25
5.2 | Lay walkways |  | 2017-11-01 | 2017-11-05 | 5 |  | 3 | 0 | 5
5.3 | Set up lawns |  | 2017-11-06 | 2017-11-07 | 2 |  | 2 | 0 | 2
5.4 | Plant saplings |  | 2017-11-06 | 2017-11-07 | 2 |  | 2 | 0 | 2
[8 empty] | 0 | 0
Note on A11: Work Breakdown Structure Enter the Task# and Subtask# 2 2.1 2.2 etc.
Note on F11: Duration (Calendar Days) Enter the number of calendar days for the given task. Refer to the Working Days column or use a calendar to determine the corresponding working days. For the main tasks, you can calculate the duration by finding the maximum End date of the sub tasks and subtracting the earliest start date. For example: F13=MAX(E14:E17)-D13
Note on G11: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%). For the main tasks, you can use a weighted average of the sub tasks by adding the formula: G13=SUMPRODUCT(F14:F17,G14:G17)/SUM(F14:F17) Note: If you insert rows, make sure that the calculation is updated correctly.