## Project Plan
# | TASK | Status | Owner | Due Date | Comments/ Dependencies
1 | Identify measures/cost savings | Ongoing | Debbie | Ongoing
2 | Track possible regulatory changes and incorporate into policies | Ongoing | John | Ongoing | State/Federal level
3 | Complete and publish Exceptions list | Complete | Kelsey | 2016-12-24
4 | Form campus advisory group | In progress | John | 2016-01-09
5 | Explore/Implement programming | In progress | Jan | 2009-01-01 | Work order is already in the pipeline, has not been prioritized Consider downstream impacts of this change
5a | DELIVERABLE: Notify campus of new PAS limit | UPDATE COMMUNICATION PLAN
6 | Create new registration form to capture key data |  | Gina | 2016-12-15 | Related to BofA project
7 | Identify challenges to moving purchases to eCommerce and how to manage them | In progress | Dave/Lori | 2009-01-01 | For example, level 3 data availability to prevent double billing for freight
8 | Analyze department purchasing methods and users, and plan to contact/train them | In progress | Dave/Customer Service Team | 2009-01-01 | Dependent on Step 7
9 | Track equipment | In progress | Dave/Erinne | 2009-01-01
9a | DELIVERABLE: communicate policy for tracking fixed assets purchased with ProCard | UPDATE COMMUNICATION PLAN